## Meeting 1
Meeting # | Date | Duration | Location | In attendance | Topic 1 |  | Topic 2 |  | Next Meeting Agenda
[5 empty] | Discussion Item | Decision Made | Discussion Item | Decision Made
1 | 2025-01-24 | 1 hour | Hall building | Arham Akram, Aboubacry Ba, Emre Emuler, Irfan Nafiun Islam, CJ Christian Jeune, Ali Hani Ali Marei Khalifa | The team discussed the programming languages and technologies each member is familiar with to determine the most suitable ones for the project. | The team decided to use Firebase for the back-end, along with HTML, CSS, and JavaScript for the front-end. | The team discussed who would be responsible for creating the GitHub repository to organize project deliverables. | It was decided that Ali will create the GitHub repository and set up the initial project structure. | The team will discuss the user stories for Sprint 1.

## Meeting 2
Meeting # | Date | Duration | Location | In attendance | Topic 1 |  | Topic 2 |  | Topic 3 |  | Next Meeting Agenda
[5 empty] | Discussion Item | Decision Made | Discussion Item | Decision Made | Discussion Item | Decision Made
2 | 2025-01-27 | 1 hour | Online | Arham Akram, Aboubacry Ba, Emre Emuler, Irfan Nafiun Islam, CJ Christian Jeune, Ali Hani Ali Marei Khalifa | The team defined user stories for Sprint 1, focusing on functionalities related to user authentication, the homepage, and role management for admin and regular users. | The team created four user stories along with their descriptions. | The team discussed how to estimate story points for each task to measure effort. | The team decided to estimate story points based on two main factors: task complexity and the time needed to complete the task. | The team discussed the task breakdown based on the created user stories to organize the development activities. | The team divided each user story into specific tasks, assigning them to team members based on each member's strengths and preferences. | The team will discuss the acceptance flow and acceptance criteria for each user story.

## Meeting 3
Meeting # | Date | Duration | Location | In attendance | Topic 1 |  | Topic 2 |  | Next Meeting Agenda
[5 empty] | Discussion Item | Decision Made | Discussion Item | Decision Made
3 | 2025-01-29 | 25 minutes | Online | Arham Akram, Aboubacry Ba, Emre Emuler, Irfan Nafiun Islam, CJ Christian Jeune, Ali Hani Ali Marei Khalifa | The team discussed how to structure the acceptance flow for each user story. | The team decided to adopt an acceptance flow that ensures review and thorough testing. Validation will be required before marking a user story as complete. | The team discussed how to create clear, testable acceptance criteria for each user story. | The team agreed to define acceptance criteria as a list of specific conditions that must be met for a user story to be considered complete. | The team will discuss priority levels and risks for each task.

## Meeting 4
Meeting # | Date | Duration | Location | In attendance | Topic 1 |  | Topic 2 |  | Next Meeting Agenda
[5 empty] | Discussion Item | Decision Made | Discussion Item | Decision Made
4 | 2025-01-30 | 15 minutes | Online | Arham Akram, Aboubacry Ba, Emre Emuler, Irfan Nafiun Islam, CJ Christian Jeune, Ali Hani Ali Marei Khalifa | The team discussed which tasks should be assigned higher priority based on their importance to the project. | The team assigned priority levels to each task, using three options: high, medium, and low. | The team discussed the potential risks associated with each task to identify challenges that could affect progress. | The team evaluated risks for each task, categorizing them as low, medium, or high, and documented explanations for the identified risks. | The team will review Sprint 1 progress and address any issues.

## Meeting 5
Meeting # | Date | Duration | Location | In attendance | Topic 1 |  | Topic 2 |  | Next Meeting Agenda
[5 empty] | Discussion Item | Decision Made | Discussion Item | Decision Made
5 | 2025-01-74 | 1 hour | Hall building | Arham Akram, Aboubacry Ba, Emre Emuler, Irfan Nafiun Islam, CJ Christian Jeune, Ali Hani Ali Marei Khalifa | The team reviewed the progress of Sprint 1 to assess the status of ongoing tasks. | The team identified that documentation tasks were on track, while coding tasks were behind schedule, requiring additional attention to meet sprint deadlines. | The team discussed issues affecting task completion, specifically a problem with the login functionality. | The team identified the cause of the login issue and successfully fixed it during the meeting, allowing development to proceed. | The team will review the documentation progress and identify any remaining tasks to be completed.

## Meeting 6
Meeting # | Date | Duration | Location | In attendance | Topic 1 |  | Topic 2 |  | Next Meeting Agenda
[5 empty] | Discussion Item | Decision Made | Discussion Item | Decision Made
6 | 2025-01-74 | 20 minutes | Online | Arham Akram, Aboubacry Ba, Emre Emuler, Irfan Nafiun Islam, CJ Christian Jeune, Ali Hani Ali Marei Khalifa | The team reviewed the documentation progress to assess what sections were completed and what still needed work. | The team identified incomplete sections and assigned final documentation tasks to ensure everything was completed before the deadline. | The team discussed potential improvements and additional features for the project. | The team decided to add a profile section to provide personalized account management. | The team will discuss the merging process for all feature branches into the main branch and address conflicts.

## Meeting 7
Meeting # | Date | Duration | Location | In attendance | Topic 1 |  | Topic 2 |  | Next Meeting Agenda
[5 empty] | Discussion Item | Decision Made | Discussion Item | Decision Made
7 | 2025-02-06 | 30 minutes | Online | Arham Akram, Aboubacry Ba, Emre Emuler, Irfan Nafiun Islam, CJ Christian Jeune, Ali Hani Ali Marei Khalifa | The team discussed the process for merging code to ensure a functional integration into the main branch of different features. | The team agreed to follow a structured workflow, requiring all changes to go through code reviews before merging into the main branch, with code merged in a predefined order. | The team addressed potential merge conflicts and strategies to resolve them efficiently. | The team decided that before merging, each member will pull the latest changes and test their code locally. This approach ensures conflicts are resolved in advance, preventing issues in the main branch. | The team will test the merged code to ensure all functionalities work correctly and finalize the documentation.

## Meeting 8
Meeting # | Date | Duration | Location | In attendance | Topic 1 |  | Topic 2 |  | Next Meeting Agenda
[5 empty] | Discussion Item | Decision Made | Discussion Item | Decision Made
8 | 2025-02-07 | 45 minutes | Online | Arham Akram, Aboubacry Ba, Emre Emuler, Irfan Nafiun Islam, CJ Christian Jeune, Ali Hani Ali Marei Khalifa | The team discussed the process for testing the merged code to ensure all functionalities work as expected. | The team conducted tests on all Sprint1 features and fixed any issues to ensure the system worked as expected. | The team discussed finalizing the Sprint1 documentation, ensuring all required deliverables, such as the sprint plan, user stories, task breakdown, meeting minutes, and contribution logs, were complete. | The team reviewed and updated the documentation. It was divided among team members, who verified that all files were correctly structured in the GitHub repository. | The team will start planning Sprint2.