## Sheet1
Meeting # | Date | Duration | Location | In attendance | Topic 1 |  | Topic 2 |  | Next Meeting Agenda
[5 empty] | Discussion Item | Decision Made | Discussion Item | Decision Made
1 | 2025-01-24 | 1 hour | Hall building | Arham Akram, Aboubacry Ba, Emre Emuler, Irfan Nafiun Islam, CJ Christian Jeune, Ali Hani Ali Marei Khalifa | The team discussed the programming languages and technologies each member is familiar with to determine the most suitable ones for the project. | The team decided to use Firebase for the back-end, along with HTML, CSS, and JavaScript for the front-end. | The team discussed who would be responsible for creating the GitHub repository to organize project deliverables. | It was decided that Ali will create the GitHub repository and set up the initial project structure. | The team will discuss the user stories for Sprint 1.