## Sheet1
Meeting # | Date | Duration | Location | In attendance | Topic 1 |  | Topic 2 |  | Topic 3 |  | Next Meeting Agenda
[5 empty] | Discussion Item | Decision Made | Discussion Item | Decision Made | Discussion Item | Decision Made
2 | 2025-01-27 | 1 hour | Online | Arham Akram, Aboubacry Ba, Emre Emuler, Irfan Nafiun Islam, CJ Christian Jeune, Ali Hani Ali Marei Khalifa | The team defined user stories for Sprint 1, focusing on functionalities related to user authentication, the homepage, and role management for admin and regular users. | The team created four user stories along with their descriptions. | The team discussed how to estimate story points for each task to measure effort. | The team decided to estimate story points based on two main factors: task complexity and the time needed to complete the task. | The team discussed the task breakdown based on the created user stories to organize the development activities. | The team divided each user story into specific tasks, assigning them to team members based on each member's strengths and preferences. | The team will discuss the acceptance flow and acceptance criteria for each user story.