## Sheet1
Meeting # | Date | Duration | Location | In attendance | Topic 1 |  | Topic 2 |  | Next Meeting Agenda
[5 empty] | Discussion Item | Decision Made | Discussion Item | Decision Made
5 | 2025-01-74 | 1 hour | Hall building | Arham Akram, Aboubacry Ba, Emre Emuler, Irfan Nafiun Islam, CJ Christian Jeune, Ali Hani Ali Marei Khalifa | The team reviewed the progress of Sprint 1 to assess the status of ongoing tasks. | The team identified that documentation tasks were on track, while coding tasks were behind schedule, requiring additional attention to meet sprint deadlines. | The team discussed issues affecting task completion, specifically a problem with the login functionality. | The team identified the cause of the login issue and successfully fixed it during the meeting, allowing development to proceed. | The team will review the documentation progress and identify any remaining tasks to be completed.