## Sheet1
Meeting # | Date | Duration | Location | In attendance | Topic 1 |  | Topic 2 |  | Next Meeting Agenda
[5 empty] | Discussion Item | Decision Made | Discussion Item | Decision Made
6 | 2025-01-74 | 20 minutes | Online | Arham Akram, Aboubacry Ba, Emre Emuler, Irfan Nafiun Islam, CJ Christian Jeune, Ali Hani Ali Marei Khalifa | The team reviewed the documentation progress to assess what sections were completed and what still needed work. | The team identified incomplete sections and assigned final documentation tasks to ensure everything was completed before the deadline. | The team discussed potential improvements and additional features for the project. | The team decided to add a profile section to provide personalized account management. | The team will discuss the merging process for all feature branches into the main branch and address conflicts.